# LingoPure Technical Migration & Infrastructure Ownership Plan

Date: 11 September 2026
Prepared by: Dennis McMahon
Audience: Minh and LingoPure Management
Status: DRAFT — FOR REVIEW AND APPROVAL BEFORE EXECUTION

## 1. Purpose of this document

This document defines the proposed technical migration of the LingoPure application from infrastructure controlled by Corporate AI Solutions / Dennis to infrastructure owned and controlled by LingoPure.

The objective is not simply to transfer the GitHub repository.

The intended end state is that LingoPure has operational ownership and administrative control of:

- GitHub

- Vercel

- Supabase

- production domains

- application secrets and credentials

- CI/CD

- production application data

- authentication

- storage

- deployment infrastructure

The migration is designed to be performed in controlled stages, with validation and rollback points between each stage.

No production migration or destructive change should be undertaken until this document has been reviewed and approved by Minh/LingoPure management.

# 2. Executive summary

The current LingoPure application is distributed across infrastructure controlled by Dennis/CAS.

The proposed migration is:

CURRENT STATE
=============

CAS / Dennis
     │
     ├── GitHub
     │     └── caistech/LingoPureAI
     │
     ├── Vercel
     │     └── lingo-pure-ai
     │
     ├── Supabase
     │     └── nbvprbaumwmfczsfcyrv
     │
     ├── Domains / DNS
     │
     └── CI/CD credentials
     
              │
              │ MIGRATION
              ▼

TARGET STATE
============

LingoPure
     │
     ├── GitHub
     │     └── LingoPure/lingopure
     │
     ├── Vercel
     │     └── LingoPure-owned project
     │
     ├── Supabase
     │     └── LingoPure-owned project
     │
     ├── Production domain
     │     └── LingoPure-controlled
     │
     └── CI/CD + production credentials
           └── LingoPure-controlled

The migration should not be treated as one large cutover.

It should be performed as a series of independently validated stages:

- Approval and preparation

- GitHub transfer

- LingoPure Vercel environment creation

- LingoPure Supabase environment creation

- Database/authentication/storage migration

- Vercel → Supabase integration

- Domain/DNS migration

- Production cutover

- Post-cutover validation

- Decommissioning of superseded CAS infrastructure

# 3. Important architectural boundary

There is an important distinction between LingoPure application ownership and the CAS shared technology substrate.

The LingoPure application currently consumes private @caistech/* packages from the CAS GitHub Packages registry.

The proposed infrastructure migration does not automatically require those packages to be renamed or forked.

The initial proposed architecture is therefore:

LingoPure-owned application
        │
        ├── LingoPure GitHub
        ├── LingoPure Vercel
        ├── LingoPure Supabase
        └── LingoPure domain
                │
                ▼
          LingoPure application
                │
                ▼
       @caistech/* shared packages
                │
                ▼
       CAS cais-shared-services

This means:

LingoPure owns and operates its product and infrastructure while continuing, initially, to consume the shared CAS technology substrate.

A future decision can determine whether the packages themselves should be carved out and transferred to LingoPure.

That decision should be treated separately because combining a package/substrate migration with the infrastructure migration materially increases risk.

# 4. Decisions requiring approval

Before execution, Minh/LingoPure should explicitly approve the following.

| Decision | Proposed position |
| --- | --- |
| GitHub ownership | Transfer application repository to LingoPure GitHub organisation |
| Vercel ownership | Create/use LingoPure-owned Vercel team/account |
| Supabase ownership | Create/use LingoPure-owned Supabase organisation/project |
| Production domain | Move to LingoPure-controlled domain/DNS |
| CI/CD | Move required secrets and variables to LingoPure-controlled GitHub/Vercel environments |
| Application database | Migrate from CAS Supabase to LingoPure Supabase |
| Authentication | Migrate/validate as part of Supabase migration |
| Storage | Migrate buckets, objects and policies |
| CAS shared packages | Remain CAS-owned initially |
| @lingopure/* package carve-out | Not part of this migration unless separately approved |
| Old CAS infrastructure | Retain temporarily for rollback, then decommission after agreed stability period |

# 5. Current-state inventory

| Component | Current state |
| --- | --- |
| GitHub repository | caistech/LingoPureAI |
| Target GitHub repository | LingoPure/lingopure |
| Vercel project | lingo-pure-ai |
| Vercel URL | lingo-pure-ai.vercel.app |
| Current Vercel team | Corporate AI Solutions |
| Supabase project | nbvprbaumwmfczsfcyrv |
| Supabase region | Tokyo |
| Shared packages | @caistech/* |
| Shared package source | caistech/cais-shared-services |
| Package registry | GitHub Packages |
| Application source | Next.js |
| Package manager | npm / package-lock.json |
| CI/CD | GitHub Actions + Vercel |
| Authentication | Supabase Auth |
| Production domain | To be confirmed as part of migration |
| Existing application data | Current CAS Supabase project |

# 6. Target ownership model

The desired final state is:

| Asset | Target owner |
| --- | --- |
| LingoPure GitHub organisation | LingoPure |
| LingoPure application repository | LingoPure |
| GitHub Actions | LingoPure |
| GitHub repository secrets | LingoPure |
| Vercel organisation/team | LingoPure |
| Vercel project | LingoPure |
| Vercel environment variables | LingoPure |
| Production domain | LingoPure |
| DNS | LingoPure |
| Supabase organisation | LingoPure |
| Supabase production project | LingoPure |
| Application database | LingoPure |
| Supabase Auth | LingoPure |
| Supabase Storage | LingoPure |
| Production credentials | LingoPure |
| CAS shared services | CAS |
| cais-shared-services | CAS |
| @caistech/* packages | CAS initially |

# 7. Migration principles

The migration should follow these principles:

### 7.1 No unnecessary production downtime

The existing production system remains operational while the new LingoPure infrastructure is prepared.

### 7.2 Build before cutover

The new GitHub/Vercel/Supabase environment should be constructed and tested before production DNS or application traffic is moved.

### 7.3 Preserve rollback

The current CAS environment should not be deleted immediately.

It becomes the rollback environment until the new LingoPure environment has operated successfully for an agreed period.

### 7.4 Validate each layer independently

GitHub, Vercel, Supabase, authentication, storage, email, application functionality and DNS should each be validated separately.

### 7.5 No credential sharing where avoidable

LingoPure should receive its own credentials and administrative access.

Dennis should not remain the operational dependency for routine LingoPure production administration.

# 8. Phase 0 — Approval and preparation

Estimated time: 30–60 minutes

No production changes occur during this phase.

## 8.1 Confirm LingoPure accounts

Before migration begins, confirm that LingoPure has:

- GitHub organisation

- GitHub organisation owner

- Vercel account/team

- Vercel billing/plan

- Supabase organisation

- Supabase billing/plan

- domain/DNS access

- required administrators

## 8.2 Confirm personnel

At least one LingoPure administrator should have administrative access to:

- GitHub

- Vercel

- Supabase

- DNS/domain

- production email/integration services where applicable

## 8.3 Create migration backups

Before modifying production:

- database backup

- storage inventory

- configuration inventory

- environment variable inventory

- GitHub repository backup

- Vercel configuration inventory

- Supabase configuration inventory

## 8.4 Record current production state

Record:

- current Git commit

- current Vercel deployment

- current Supabase project

- current production domain

- current environment variables

- current package versions

- current database migration state

## 8.5 Migration approval gate

STOP HERE.

Minh/LingoPure approves the migration plan before execution continues.

# 9. Phase 1 — GitHub migration

Estimated time: 15–30 minutes

## 9.1 Pre-migration repository check

The current repository contains:

- full Git history

- current branches

- GitHub Actions

- Dependabot configuration

- private @caistech/* package dependencies

There is also known unmerged work:

f573ebb fix(privacy): disclose overseas storage

This commit is currently ahead of origin/main.

Before migration/deployment:

- merge the privacy fix into main, or

- create a PR and merge it after review

- commit or stash outstanding working-tree changes

- ensure no required work exists only on Dennis’s local machine

This should be treated as a pre-migration blocker.

## 9.2 Transfer repository

Dennis initiates the transfer:

gh repo transfer caistech/LingoPureAI LingoPure --new-name lingopure

Target:

https://github.com/LingoPure/lingopure

## 9.3 LingoPure acceptance

A LingoPure GitHub organisation owner accepts the repository transfer.

## 9.4 Repository validation

Confirm:

LingoPure/lingopure

contains:

- main

- Git history

- branches required for development

- tags

- issues

- pull requests

- Actions workflows

- Dependabot configuration

## 9.5 Access

Add Dennis back as a collaborator with appropriate permissions during the transition.

Long-term permissions should subsequently be reviewed by LingoPure.

# 10. Phase 2 — GitHub Actions and package access

Estimated time: 20–30 minutes

Repository transfer does not automatically transfer organisation-level secrets.

The following must be recreated under the LingoPure GitHub organisation or repository as appropriate.

## 10.1 Actions secrets

| Secret | Purpose |
| --- | --- |
| CAISTECH_PACKAGES_TOKEN | Private @caistech/* package installation |
| GITHUB_PACKAGES_TOKEN | GitHub Packages access |
| NEXT_PUBLIC_SUPABASE_URL | Supabase connection |
| SUPABASE_SERVICE_ROLE_KEY | Server-side Supabase access |
| QA_TEST_USER_ID | Voice/memory-loop testing |
| CONVAI_TOOL_SECRET | Voice webhook protection |
| ANTHROPIC_API_KEY | Claude workflow |
| GH_PAT | GitHub automation |
| EASY_CLAUDE_API_KEY | Easy-Claude-Code integration |

The exact secret list should be revalidated against the current workflow files immediately before migration.

## 10.2 Actions variables

| Variable | Purpose |
| --- | --- |
| PORTFOLIO_GATE_PREVIEW_URL | Portfolio gate smoke testing |

## 10.3 Dependabot

If Dependabot requires package credentials, recreate the relevant Dependabot secret separately.

## 10.4 Package authentication

The application currently consumes six private packages:

- @caistech/corporate-components

- @caistech/dataroom-core

- @caistech/elevenlabs-convai

- @caistech/sayfix-embed

- @caistech/webmcp-kit

- portfolio-gate package

The repository .npmrc uses NODE_AUTH_TOKEN.

No package token should ever be committed to the repository.

## 10.5 CI validation

Before proceeding:

- open a test PR

- execute GitHub Actions

- confirm npm ci

- confirm private package installation

- confirm gate workflow

- confirm no 401/403 errors

GO / NO-GO CHECKPOINT

GitHub must be operational before Vercel migration proceeds.

# 11. Phase 3 — Create LingoPure Vercel environment

Estimated time: 20–40 minutes

The existing Vercel project should not simply be transferred if the objective is full LingoPure infrastructure ownership.

Instead, prepare the LingoPure Vercel environment first.

## 11.1 Create/confirm LingoPure Vercel team

Confirm:

- LingoPure owns the team/account

- billing is controlled by LingoPure

- Minh has appropriate administrative access

- required developers have access

## 11.2 Create/import the project

Create/import the application as:

lingo-pure-ai

Connect it to:

LingoPure/lingopure

Production branch:

main

## 11.3 Recreate Vercel environment variables

The existing project currently contains values including:

GITHUB_PACKAGES_TOKEN
NODE_AUTH_TOKEN
NEXT_PUBLIC_SUPABASE_URL
NEXT_PUBLIC_SUPABASE_ANON_KEY
SUPABASE_SERVICE_ROLE_KEY
ANTHROPIC_API_KEY
OPENAI_API_KEY
ELEVENLABS_API_KEY
ELEVENLABS_AGENT_ID
ELEVENLABS_WEBHOOK_SECRET
RESEND_API_KEY
EMPLOYER_DEMO_PASSWORD
HEYGEN_API_KEY
NEXT_PUBLIC_INVESTOR_MORGAN_AGENT_ID
NEXT_PUBLIC_CANVAS_MODE
ADMIN_EMAILS

The final list must be verified against the current production project before migration.

Each variable should be classified as:

- Development

- Preview

- Production

Do not assume that a variable should automatically have the same value in all three environments.

## 11.4 Vercel build configuration

Verify:

- Node version

- build command

- install command

- output configuration

- environment configuration

- Git integration

- production branch

The application currently uses npm and package-lock.json.

## 11.5 Preview deployment

Deploy the new LingoPure Vercel project without changing production DNS.

Validate:

- build

- application startup

- package installation

- Supabase connectivity

- authentication

- dashboard

- application routes

- voice

- investor functionality

- HR functionality

# 12. Phase 4 — Create LingoPure Supabase project

Estimated time: 30–60 minutes plus migration time

Create a new Supabase organisation/project controlled by LingoPure.

Preferably use the same geographic region as the existing project:

Tokyo / Northeast Asia

## 12.1 Create target project

Record:

- project reference

- project URL

- anon key

- service-role key

- database connection information

These credentials must be stored securely.

## 12.2 Apply database schema

The source repository contains the Supabase migration files.

The preferred process is:

- create target project

- inspect current production schema

- verify migration history

- apply/replay required migrations

- validate resulting schema

Do not assume the migration folder alone is sufficient.

The current production database should be compared with the repository migrations before cutover.

## 12.3 Database objects to validate

Validate:

- tables

- columns

- indexes

- constraints

- foreign keys

- functions

- triggers

- RLS policies

- extensions

- database roles

- scheduled jobs where applicable

## 12.4 Data migration

Migrate the required production data from the existing project.

The exact method should be selected after reviewing database size and current Supabase capabilities.

Potential methods include:

- Supabase database dump/restore

- PostgreSQL dump/restore

- controlled table migration

The selected method must preserve:

- IDs

- relationships

- timestamps

- application state

- required metadata

# 13. Phase 5 — Supabase Authentication migration

CRITICAL

Authentication must be treated separately from ordinary database migration.

The target environment must be tested for existing-user authentication before production cutover.

Review and migrate/configure:

- users

- identities

- authentication providers

- email configuration

- redirect URLs

- site URL

- password reset

- magic-link authentication

- confirmation emails

- OAuth configuration if applicable

The current application uses:

supabase/config.toml

and currently references:

lingo-pure-ai.vercel.app

These settings must be reviewed and updated as part of the final domain migration.

## Authentication acceptance test

At minimum test:

- existing user sign-in

- new user signup if enabled

- magic link

- password reset

- redirect after authentication

- dashboard access

- logout/login cycle

No production cutover should occur until this passes.

# 14. Phase 6 — Supabase Storage migration

Inventory all storage buckets.

For each bucket migrate/validate:

- bucket name

- public/private setting

- objects

- metadata

- policies

- access controls

Test application functions that read/write storage.

# 15. Phase 7 — Other Supabase services

Inventory and migrate any:

- Edge Functions

- webhooks

- database webhooks

- scheduled functions

- cron jobs

- secrets

- extensions

- integrations

These should not be assumed from the database schema.

# 16. Phase 8 — Connect LingoPure Vercel to LingoPure Supabase

Once the new Supabase environment has been validated:

Update the LingoPure Vercel project.

Required variables include:

NEXT_PUBLIC_SUPABASE_URL
NEXT_PUBLIC_SUPABASE_ANON_KEY
SUPABASE_SERVICE_ROLE_KEY

Also update relevant GitHub Actions secrets.

Then deploy again.

## Validation

Confirm:

- application connects to new Supabase

- existing user can authenticate

- dashboard loads

- application data appears correctly

- writes work

- storage works

- voice functionality works

- investor functionality works

- HR functionality works

# 17. Phase 9 — Production domain migration

The current Vercel URL may continue to be used temporarily during migration.

The final production environment should use a LingoPure-controlled domain, for example:

app.lingopure.com

or another domain/subdomain selected by LingoPure.

## Before DNS cutover

Configure the new domain in LingoPure Vercel.

Verify:

- SSL

- DNS

- Vercel domain configuration

- Supabase site_url

- Supabase redirect URLs

- authentication callback URLs

- email links

- password-reset URLs

- application configuration

- third-party callbacks

## DNS cutover

Only after the new Vercel + Supabase environment passes the complete test suite:

- change DNS

- wait for propagation

- validate HTTPS

- validate application

- validate authentication

- validate application integrations

The old Vercel environment remains available during the agreed rollback period.

# 18. Phase 10 — Production cutover

This is the formal GO/NO-GO point.

## Required checks

### GitHub

- LingoPure/lingopure operational

- main contains privacy fix or later

- CI passes

- private packages install successfully

- Dependabot configured

### Vercel

- LingoPure owns Vercel team

- project connected to LingoPure GitHub

- all production variables verified

- production deployment green

### Supabase

- LingoPure owns Supabase project

- schema validated

- production data migrated

- authentication validated

- storage validated

- policies validated

- functions/webhooks validated

### Domain

- LingoPure owns domain/DNS

- SSL active

- Supabase redirects updated

- authentication tested

### Application

- sign-in

- dashboard

- classroom

- investor

- HR

- voice

- email

- storage

- relevant external integrations

### Security

- production secrets are LingoPure-controlled

- no credentials committed to repository

- Dennis/CAS credentials are not required for routine operation

# 19. Rollback plan

The migration should retain the current CAS infrastructure until the new environment is confirmed stable.

If a critical problem occurs:

LingoPure production
       │
       ▼
Identify failure
       │
       ▼
Rollback DNS / deployment
       │
       ▼
Existing CAS environment
       │
       ▼
Restore service

Rollback may involve:

- reverting DNS

- restoring previous Vercel deployment

- reconnecting the previous environment

- reverting Supabase application configuration

The exact rollback mechanism should be documented immediately before production cutover.

# 20. Post-cutover monitoring period

After successful cutover:

Do not immediately delete the old CAS infrastructure.

Recommended approach:

### Day 0

Full production validation.

### Days 1–3

Monitor:

- authentication

- application errors

- database errors

- Vercel deployments

- Supabase logs

- email

- voice

- storage

- external integrations

### Days 4–14

Normal production monitoring.

If stable, obtain final confirmation from LingoPure.

Only then begin decommissioning the old CAS infrastructure.

The precise retention period should be approved before cutover.

# 21. Decommissioning CAS infrastructure

Once the migration has been stable for the agreed period:

- remove obsolete Vercel project/configuration

- remove obsolete CAS production secrets where appropriate

- remove obsolete DNS configuration

- revoke credentials no longer required

- document final infrastructure

- confirm LingoPure has administrator access everywhere

- retain required backups

Do not delete the original Supabase project until the agreed retention/backup period has expired.

# 22. @caistech/* shared package decision

The current application consumes private CAS packages.

### Recommended initial position

Continue using:

@caistech/*

from:

caistech/cais-shared-services

This avoids unnecessarily combining two major migrations.

The LingoPure application can therefore be independently hosted while continuing to consume the shared CAS technology layer.

### Future option

If LingoPure eventually needs complete technical independence:

@caistech/*
        ↓
@lingopure/*

This would require a separate project covering:

- package extraction

- package repository creation

- scope changes

- package publishing

- source import changes

- .npmrc

- GitHub Actions

- Dependabot

- versioning

- testing

This is not part of the current migration unless separately approved.

# 23. Security and credential ownership

The target state must eliminate operational dependence on Dennis’s personal credentials.

LingoPure should control:

- GitHub organisation credentials

- Vercel credentials

- Supabase credentials

- domain/DNS credentials

- production API credentials

- application secrets

- deployment credentials

Where CAS services remain dependencies, they should use appropriately scoped service credentials rather than personal credentials wherever practical.

# 24. Known migration risks

| Risk | Mitigation |
| --- | --- |
| GitHub transfer rejected | LingoPure org owner accepts transfer |
| GitHub Actions secrets disappear | Recreate under LingoPure |
| Private package installation fails | Validate CAISTECH_PACKAGES_TOKEN before Vercel cutover |
| Vercel build fails | Preview deploy before DNS migration |
| Supabase schema mismatch | Compare production schema against migrations |
| Authentication breaks | Dedicated authentication migration/testing |
| Storage objects missing | Separate bucket/object migration and validation |
| Magic links fail | Update Supabase site/redirect URLs |
| DNS issues | Configure domain before cutover and retain old URL |
| Data loss | Full database/storage backup before migration |
| Application regression | Full production smoke-test checklist |
| Rollback required | Keep CAS infrastructure operational during transition |
| Scope creep into package migration | Keep @caistech/* migration separate |

# 25. Definition of Done

The migration is complete when:

## Ownership

- LingoPure owns the GitHub repository

- LingoPure owns the Vercel team/project

- LingoPure owns the Supabase organisation/project

- LingoPure controls the production domain/DNS

- LingoPure controls production credentials

## GitHub

- LingoPure/lingopure exists

- main is production source of truth

- privacy fix is merged

- CI passes

- private packages install

- Dependabot works

## Vercel

- LingoPure Vercel project connected to LingoPure GitHub

- Development environment verified

- Preview environment verified

- Production environment verified

- all required environment variables recreated

- production deployment green

## Supabase

- LingoPure project created

- database schema migrated

- production data migrated

- RLS policies validated

- authentication migrated/validated

- storage migrated

- functions/webhooks/jobs validated

## Domain

- LingoPure production domain configured

- SSL verified

- DNS cutover complete

- Supabase redirects updated

- magic links/password reset tested

## Application

- sign-in

- dashboard

- classroom

- investor

- HR

- voice

- email

- storage

- external integrations

## Operational independence

- Minh can deploy

- Minh can manage Vercel

- Minh can manage Supabase

- Minh can manage GitHub

- LingoPure does not require Dennis for routine infrastructure administration

- old CAS infrastructure retained only for agreed rollback period

# 26. What is explicitly NOT part of this migration

Unless separately approved, this project does not include:

- redesigning the LingoPure application

- changing the application architecture

- rewriting the shared CAS substrate

- renaming @caistech/*

- creating @lingopure/*

- changing application functionality

- changing business logic

- changing the LingoPure product roadmap

- migrating unrelated CAS infrastructure

- transferring cais-shared-services

The purpose of this migration is ownership and infrastructure separation, not product redevelopment.

# 27. Reference — current repositories and infrastructure

| Resource | Current |
| --- | --- |
| Current repository | https://github.com/caistech/LingoPureAI |
| Target repository | https://github.com/LingoPure/lingopure |
| LingoPure GitHub organisation | https://github.com/LingoPure |
| Current Vercel project | lingo-pure-ai |
| Current Vercel URL | https://lingo-pure-ai.vercel.app/ |
| Current Supabase project | nbvprbaumwmfczsfcyrv |
| Supabase region | Tokyo |
| GitHub Packages | https://npm.pkg.github.com |
| Shared CAS repository | caistech/cais-shared-services |
| Supabase configuration | supabase/config.toml |

# 28. Key files requiring review before execution

The following files should be reviewed against the final migration checklist:

.github/workflows/gate.yml
.github/workflows/health-sensors.yml
.github/workflows/hr-module.yml
.github/workflows/claude-code.yml
.github/dependabot.yml
package.json
package-lock.json
.npmrc
supabase/config.toml

The final environment-variable and secret inventory should be generated from the actual current deployment/workflows immediately before execution rather than relying solely on this document.

# 29. Execution responsibility

### Dennis

Responsible for:

- preparing the source environment

- repository transfer

- providing current configuration/secret values securely

- assisting with migration

- troubleshooting migration issues

- maintaining rollback capability during transition

### Minh / LingoPure

Responsible for:

- approving this migration plan

- creating/owning LingoPure infrastructure

- controlling LingoPure accounts and billing

- accepting GitHub transfer

- creating/owning Vercel environment

- creating/owning Supabase environment

- validating production environment

- approving production cutover

- taking ongoing operational ownership

# 30. Final approval

The migration should not begin until the following has been agreed:

### LingoPure Management Approval

Migration plan approved:
☐ Yes
☐ No
☐ Changes required

GitHub migration approved:
☐ Yes
☐ No

Vercel migration approved:
☐ Yes
☐ No

Supabase migration approved:
☐ Yes
☐ No

Production domain migration approved:
☐ Yes
☐ No

Continue using CAS @caistech/* packages initially:
☐ Yes
☐ No
☐ Separate decision required

Approved by: ______________________________

Date: ______________________________

Comments / required changes:

# 31. Proposed execution sequence after approval

Once approved, the actual implementation sequence will be:

1. APPROVAL
      │
      ▼
2. BACKUP + INVENTORY
      │
      ▼
3. GITHUB TRANSFER
      │
      ▼
4. GITHUB ACTIONS / SECRETS
      │
      ▼
5. CREATE LINGOPURE VERCEL
      │
      ▼
6. CREATE LINGOPURE SUPABASE
      │
      ▼
7. MIGRATE DATABASE
      │
      ▼
8. MIGRATE AUTH + STORAGE
      │
      ▼
9. CONNECT VERCEL → NEW SUPABASE
      │
      ▼
10. FULL APPLICATION TEST
      │
      ▼
11. CONFIGURE LINGOPURE DOMAIN
      │
      ▼
12. GO / NO-GO
      │
      ▼
13. DNS / PRODUCTION CUTOVER
      │
      ▼
14. MONITOR + VALIDATE
      │
      ▼
15. RETAIN OLD ENVIRONMENT
    FOR AGREED ROLLBACK PERIOD
      │
      ▼
16. DECOMMISSION CAS PRODUCTION INFRASTRUCTURE

The migration is complete only when LingoPure can operate, deploy, administer and recover the production application without depending on Dennis/CAS for routine infrastructure access.