MALAYSIA EXPANSION

Next Steps & Execution Agenda

Daniel × Shamini  |  September 2026

MEETING OBJECTIVE Move Malaysia from preparation into active market testing, with the sales infrastructure, target accounts and outreach ready for launch by the end of September.

# Agenda at a Glance

| # | Workstream | Decision / Output |
| --- | --- | --- |
| 1 | Malaysia Sales & Marketing Materials | Malaysia Sales Kit V1 |
| 2 | LingoPure Speaking Demo | Malaysia-ready demo flow |
| 3 | Malay Email Marketing Launch | First segmented campaign live by month-end |
| 4 | Shamini Contacts & Market Intelligence | Prioritized target-account action plan |
| 5 | Three-Company Discovery Sprint | Startup, call centre and data-centre communication maps |
| 6 | HRD Corp Partner Route | Shortlist 3–5 potential partners |
| 7 | September Execution Targets | Preparation complete, October moves to active conversion |

# 1. Malaysia Sales & Marketing Materials

Complete the core materials required before active outreach begins.

## Website

Final human review of the updated Bahasa Malaysia copy, focused on natural Malaysian wording and local business tone.

Confirm the Free Demo CTA, contact journey and any remaining Malaysia-specific changes.

Agree the final deadline for the /ms website.

## Sales Deck

Review the existing LingoPure B2B material and identify what requires Malaysia-specific localization.

Ensure messaging works for BPO, outsourcing, call centres and technical or cross-border teams.

Keep the core LingoPure proposition consistent while adapting examples to Malaysian buyers.

## Testimonials & Proof

Select the strongest existing testimonials for professional communication, confidence, meetings, international communication and measurable improvement.

Decide which proof belongs on the website, in the sales deck and in outreach.

Identify where Malaysia-specific proof should be added as pilots and customers develop.

OUTPUT: Malaysia Sales Kit V1.

# 2. LingoPure Speaking Demo

Once Dennis has the speaking/demo capability ready, test it as a commercial tool for the Malaysian market.

Shamini completes the demo first from the perspective of a Malaysian professional.

Check whether the instructions, experience and results are clear.

Define how the demo should be presented to HR, L&D and Operations decision-makers.

Build a short BPO/customer-service scenario.

Consider a separate technical/data-centre scenario.

Define what the prospect receives after the demo and how the result leads naturally into a paid pilot.

Demo Flow

Experience

Measurement

Communication Gap

Recommendation

LingoPure Solution

OUTPUT: Malaysia-ready demo and sales demonstration flow.

# 3. Malaysia Email Marketing Launch

TARGET: Launch the first Malay email marketing campaign by September 30.

Build and validate the first Malaysian email-marketing database.

Capture company, industry/type, company size, decision maker, role, email/contact details, priority and known communication need where available.

Segment the list before launch. Do not send one generic campaign to every company.

Create separate messaging at minimum for BPO/customer operations and technical/data-centre environments.

Use the Malaysia Free Demo as the primary acquisition CTA where appropriate.

Pre-Launch Sequence

List

Clean

Segment

Email Copy

Landing Page

CTA

Tracking

Test

Launch

OUTPUT: First segmented Malaysian email campaign live by month-end.

# 4. Shamini's Existing Contacts & Market Intelligence

Turn all existing research, contacts, former colleagues, company lists and introductions into an actionable Malaysia pipeline.

| Field | What We Need |
| --- | --- |
| Company / Contact | Who is the opportunity? |
| Segment | BPO, call centre, outsourcing, data centre, technical, other |
| Relationship | Warm, referral, known contact, cold |
| Need / Signal | What problem, question or buying signal already exists? |
| Decision Maker | Who owns the problem, budget or operational consequence? |
| Priority | Tier 1, Tier 2, Tier 3 or Research |
| Next Action | Personal outreach, introduction, discovery call, email, LinkedIn, research |

## Priority Logic

Tier 1: Warm and high-fit. Personal outreach first.

Tier 2: Strong fit. Personalized outreach after Tier 1.

Tier 3: Market-test accounts. Email and LinkedIn campaign.

Research: Insufficient information. Investigate before contacting.

The objective is to understand what each contact actually needs before pushing a predefined LingoPure package.

OUTPUT: Malaysia Target Account & Contact Action Plan, with every existing lead assigned a next action.

# 5. Three-Company Discovery Sprint

Validate the communication opportunity across three deliberately different operating environments.

| Archetype | Purpose |
| --- | --- |
| Startup / smaller outsourcing company | Understand communication when roles are broad, processes are evolving and employees work directly across clients, management and delivery. |
| Medium-sized call centre / BPO | Understand communication bottlenecks across recruitment, readiness, live interactions, QA, coaching and performance. |
| Data centre / technical operation | Understand technical, escalation, handover, client/vendor and cross-border communication requirements. |

For each company, map:

WORKFLOW  →  COMMUNICATION TOUCHPOINT  →  BOTTLENECK  →  BUSINESS CONSEQUENCE  →  CURRENT KPI  →  LP MEASUREMENT  →  LP SOLUTION  →  BENEFIT

Use the shortened five-question discovery framework rather than another 25-question exercise.

OUTPUT: Three validated communication maps that can become the basis for industry-specific sales propositions.

# 6. Malaysia Partner / HRD Corp Route

Explore existing HRD Corp registered training providers before committing capital to LingoPure's own Malaysian infrastructure.

| Partner Role | LingoPure Role |
| --- | --- |
| Local customer-facing relationship | Communication assessment |
| HRD administration / eligibility layer | Curriculum and programme design |
| Local commercial support | Teachers and delivery |
| Local market access | Technology and measurement |

Identify potential partners with a strong customer-facing presence and relevant employer relationships.

Assess commercial terms, operational fit and protection of LingoPure's programme, technology and delivery role.

Validate demand first. Direct Malaysian infrastructure comes later when revenue justifies it.

OUTPUT: Shortlist 3 to 5 potential HRD Corp partners.

# 7. September Execution Targets

| By September 30 | Target |
| --- | --- |
| Malaysia website V2 | Approved |
| Malaysia B2B sales deck | Ready |
| Testimonials / proof material | Ready |
| Speaking demo | Tested if Dennis's build is ready |
| 100-company database | Cleaned, segmented and prioritized |
| Warm Shamini contacts | Every contact assigned a next action |
| Personal outreach | Underway |
| Malay email campaign | Launched |
| Three-company discovery sprint | Underway |
| HRD partner shortlist | Initial shortlist identified |

SEPTEMBER FINISHES THE INFRASTRUCTURE.
OCTOBER IS ABOUT GENERATING MALAYSIAN EVIDENCE AND REVENUE.

OUTREACH  →  DISCOVERY  →  DEMO  →  PILOT  →  MEASURE  →  LEARN  →  SCALE